## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Dev Parmar Project plan
PROJECT PLAN
PROJECT NAME | Data Analytics using Python And SQL
PROJECT MANAGER | Dev Parmar
PROJECT DELIVERABLE | Project documentation , Code , Demo Video
PROJECT SCOPE
PROJECT START DATE | 2024-05-20
PROJECT END DATE | 2024-06-12
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify project problem |  | 2024-04-20 | 2024-04-20 | 1 | COMPLETED
| 1.2 Study problem |  | 2024-04-21 | 2024-04-21 | 1 | COMPLETED
| 1.3 Create a project charter |  | 2024-04-22 | 2024-04-22 | 1 | COMPLETED
| 1.4 Requirement gathering |  | 2024-04-23 | 2024-04-23 | 1 | COMPLETED
2 Planning
| 2.1 Create SRS |  | 2024-04-24 | 2024-04-26 | 2 | COMPLETED
| 2.2 Create WBS |  | 2024-04-25 | 2024-04-27 | 2 | COMPLETED
| 2.3 Create project plan |  | 2024-04-26 | 2024-04-28 | 2 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2024-05-01 | 2024-05-02 | 1 | COMPLETED
| 3.2 Build |  | 2024-05-02 | 2024-05-03 | 1 | COMPLETED
| 3.2.1 DATA |  | 2024-05-03 | 2024-05-04 | 1 | COMPLETED
| Clean data |  | 2024-05-04 | 2024-05-06 | 2 | COMPLETED
[5 empty] | 2 | COMPLETED
| Study problems |  | 2023-05-07 | 2024-05-09 | 2 | COMPLETED
| Import data |  | 2024-05-10 | 2024-05-10 | 1 | COMPLETED
| Design solution |  | 2024-05-10 | 2024-05-12 | 2 | COMPLETED
| Write conclusion |  | 2024-05-14 | 2024-05-16 | 2 | COMPLETED
| Project execution |  | 2024-05-18 | 2024-05-20 | 2 | COMPLETED
| 3.3 Testing |  | 2024-05-20 | 2024-05-22 | 2 | COMPLETED
3.3.1 Check for errors
| 4 Closure |  | 2024-06-05 | 2024-06-10 | 5 | COMPLETED